## Read Me (hidden)
Employee Experience — Annual Event Calendar & Checklist Toolkit
Benchmarked against common practice at large India-based employers (IT/ITES, BFSI, FMCG, GCCs) across festive, wellness, recognition and flagship engagement events.
What this workbook contains
Tab | Purpose
Annual Event Calendar | Month-by-month calendar of events an Employee Experience (EX) Specialist typically owns or co-owns in a large India-based company, including recurring/ongoing activities.
Event Categories | The 6 event categories used across this workbook, with definitions, scale, typical budget range and lead time — use this to classify any new event you plan.
Checklist - Large Scale Events | Planning-to-wrap-up checklist for company-wide flagship events (Annual Day, Foundation Day, Diwali Mega Celebration, Awards Night, Family Day, National Day programs).
Checklist - In-house Events | Lightweight checklist for team/floor-level or small-group events (birthdays, work anniversaries, mini festival celebrations, potlucks).
Checklist - Live Shows | Checklist for artist/performer-led entertainment (DJ nights, live bands, stand-up comedy, dance troupes) whether standalone or embedded in a larger event.
Checklist - Virtual-Hybrid Events | Checklist for townhalls, webinars and any event with a remote/streamed audience component.
Checklist - Wellness & CSR | Checklist for health, wellbeing and community/CSR-linked activities (Yoga Day, blood donation, tree plantation, mental health workshops).
Checklist - Recognition & Rewards | Checklist for nomination-based recognition programs and awards ceremonies (Employee of the Month, Long Service Awards, Annual Awards Night).
How to use it
1. | Start from the Annual Event Calendar tab and adjust dates/events to your company's actual holiday list, office locations and employee demographics.
2. | Tag each event with the right Category from the Event Categories tab.
3. | Open the matching Checklist tab, copy it per event (or just track Status/Remarks inline), and assign owners against each task.
4. | Use the Status and Remarks columns on every checklist to track planning progress; conditional formatting highlights are provided as a starting template.

## Annual Event Calendar
Annual Event Calendar — Employee Experience Specialist
Illustrative calendar based on common India Inc. practice. Align dates to your official holiday list; regional festivals vary by state/office location.
Month | Suggested Date / Window | Event Name | Category | Objective / Purpose | Target Audience | Planning Lead Time | Key Stakeholders / Owners
Ongoing (Every Month) | Throughout the month | New Joiner Induction & Welcome Kit | In-house / Office-Level Event | Smooth onboarding and first-day experience for new hires | New Joiners | Ongoing | EX Specialist, HR, IT, Facilities
Ongoing (Every Month) | As per DOB calendar | Employee Birthday Celebrations | In-house / Office-Level Event | Personal recognition and team bonding | Employees with birthdays that month | 1 week | EX Specialist / Floor Coordinators
Ongoing (Every Month) | As per anniversary date | Work Anniversary Recognition | Recognition & Rewards Event | Recognize tenure and loyalty | Employees completing service milestones | 1 week | EX Specialist, HR
Ongoing (Every Month) | Last week of month | All-Hands / Business Town Hall | Virtual / Hybrid Event | Business updates, leadership connect, Q&A | All employees (onsite + remote) | 2 weeks | EX Specialist, Leadership, Internal Comms, IT
Ongoing (Every Month) | Announced monthly | Employee of the Month Award | Recognition & Rewards Event | Recognize top performers/behaviours | All employees | 2 weeks | EX Specialist, HR, People Managers
January | 1st week | New Year Kickoff & Vision-Setting Session | In-house / Office-Level Event | Set tone/theme for the year, share goals | All employees | 2 weeks | EX Specialist, Leadership
January | 14-15 Jan | Makar Sankranti / Pongal / Lohri Celebration | In-house / Office-Level Event | Cultural inclusion, regional festival celebration | All employees (location-specific) | 2 weeks | EX Specialist, Culture Committee
January | 26 Jan | Republic Day Flag Hoisting & Patriotic Program | Large-Scale Flagship Event | National pride, community/company gathering | All employees + families (select offices) | 3-4 weeks | EX Specialist, Admin, Leadership
February | 1st week | Performance Appraisal Communication Town Hall | Virtual / Hybrid Event | Transparent communication on appraisal cycle & ratings | All employees | 2 weeks | EX Specialist, HRBP, Leadership
February | 14 Feb | Employee Appreciation Week (Valentine-themed) | In-house / Office-Level Event | Peer appreciation, gratitude cards, small treats | All employees | 1-2 weeks | EX Specialist
February | Last week | Maha Shivratri Observance (optional/regional) | In-house / Office-Level Event | Cultural/religious inclusion | Interested employees | 1 week | EX Specialist, Culture Committee
March | 1st week | Holi Celebration (Colors, DJ, Snacks) | Live Show & Entertainment | Festive bonding, cultural celebration | All employees | 4-6 weeks | EX Specialist, Vendor/DJ, Admin, Security
March | 8 Mar | International Women's Day — Panel & Felicitation | Large-Scale Flagship Event | Celebrate and empower women employees, DEI messaging | All employees, esp. women employees | 4 weeks | EX Specialist, DEI Council, Leadership
March | Last week | Financial Year-End Wrap-up & Team Recognition | Recognition & Rewards Event | Close the year, recognize contributions | All employees | 3 weeks | EX Specialist, HR, Finance
April | 1 Apr | New Financial Year Kickoff Town Hall | Virtual / Hybrid Event | Share annual business plan and priorities | All employees | 2 weeks | EX Specialist, Leadership, Internal Comms
April | 13-14 Apr | Baisakhi / Vishu / Puthandu Regional New Year | In-house / Office-Level Event | Regional cultural inclusion | All employees (location-specific) | 2 weeks | EX Specialist, Culture Committee
April | 22 Apr | Earth Day — Sustainability Drive | Wellness & CSR Event | Environmental responsibility, CSR visibility | Volunteers / all employees | 3 weeks | EX Specialist, CSR/Sustainability team
April | Ongoing | Annual Day / Foundation Day — Planning Kickoff | Large-Scale Flagship Event | Begin planning for H2 flagship celebration | Core planning committee | 6+ months out | EX Specialist, Leadership, Event Agency
May | 1 May | Labour Day Acknowledgment | In-house / Office-Level Event | Recognize operations/support staff contribution | Support staff, all employees | 1 week | EX Specialist, Admin
May | Mid-May | Summer Wellness Program (Hydration & Health Tips) | Wellness & CSR Event | Preventive health awareness in peak summer | All employees | 2-3 weeks | EX Specialist, Wellness Partner
May | Last weekend | Family Fun Day | Large-Scale Flagship Event | Involve families, strengthen belonging | Employees + families | 6-8 weeks | EX Specialist, Admin, Event Agency
June | 5 Jun | World Environment Day — Tree Plantation Drive | Wellness & CSR Event | Sustainability, community engagement | Volunteers | 3 weeks | EX Specialist, CSR team
June | 21 Jun | International Yoga Day Session | Wellness & CSR Event | Physical/mental wellbeing | All employees | 2-3 weeks | EX Specialist, Wellness Partner
June | 3rd Sunday | Father's Day Engagement Post/Activity | In-house / Office-Level Event | Light engagement, social media/intranet feature | All employees | 1 week | EX Specialist, Internal Comms
July | 1st week | Mid-Year Business Review Town Hall | Virtual / Hybrid Event | Business performance update, Q&A | All employees | 2 weeks | EX Specialist, Leadership, IT/AV
July | Mid-month | Monsoon Fun Activity / Indoor Games Day | In-house / Office-Level Event | Light engagement during monsoon season | All employees | 1-2 weeks | EX Specialist
July | 1 Jul | Doctor's Day Appreciation (if applicable) | Recognition & Rewards Event | Recognize medical/healthcare staff (sector-specific) | Healthcare/medical staff | 1 week | EX Specialist, HR
August | 15 Aug | Independence Day Flag Hoisting & Cultural Program | Large-Scale Flagship Event | National pride, patriotic cultural performances | All employees + families (select offices) | 4-6 weeks | EX Specialist, Admin, Leadership, Vendor
August | Varies (Aug) | Raksha Bandhan Celebration | In-house / Office-Level Event | Cultural bonding across teams | All employees | 2 weeks | EX Specialist, Culture Committee
August | 1st Sunday | Friendship Day Engagement | In-house / Office-Level Event | Peer bonding, light activities | All employees | 1 week | EX Specialist
August | Any 2 weeks | Blood Donation Drive | Wellness & CSR Event | CSR, community health contribution | Volunteers | 3-4 weeks | EX Specialist, CSR team, Blood Bank partner
September | 5 Sep / 15 Sep | Teacher's Day / Engineer's Day Recognition | Recognition & Rewards Event | Recognize mentors / technical talent | All employees | 2 weeks | EX Specialist, HR
September | Varies | Ganesh Chaturthi Celebration | In-house / Office-Level Event | Cultural/religious inclusion | All employees (location-specific) | 2-3 weeks | EX Specialist, Culture Committee
September | Full month | Employee Engagement Week (Multi-activity) | Large-Scale Flagship Event | Sustained engagement push, multiple mini-events | All employees | 6-8 weeks | EX Specialist, Leadership, Culture Committee
September | Varies | Onam Celebration (esp. Kerala offices) | In-house / Office-Level Event | Regional cultural inclusion | All employees (location-specific) | 3 weeks | EX Specialist, Culture Committee
October | Varies | Dussehra Celebration | In-house / Office-Level Event | Cultural celebration | All employees | 2-3 weeks | EX Specialist, Culture Committee
October | 10 Oct | World Mental Health Day Workshop | Wellness & CSR Event | Mental health awareness and support | All employees | 3 weeks | EX Specialist, Wellness/EAP Partner
October | Last 2 weeks | Annual Day / Foundation Day (Grand Celebration) | Large-Scale Flagship Event | Flagship company-wide celebration, culture showcase | All employees + families | 10-12 weeks | EX Specialist, Leadership, Event Agency, Admin
October | Last week | Diwali Prep — Office Decoration Contest | In-house / Office-Level Event | Build festive anticipation, team creativity | All employees | 2 weeks | EX Specialist, Culture Committee
November | Varies (Diwali) | Diwali Mega Celebration (Lights, Mithai, Family Invite) | Large-Scale Flagship Event | Marquee festive celebration of the year | All employees + families | 10-12 weeks | EX Specialist, Leadership, Event Agency, Vendor
November | 14 Nov | Children's Day — Bring Your Kids to Work | In-house / Office-Level Event | Family inclusion, light-hearted engagement | Employees with children | 3-4 weeks | EX Specialist, Admin
November | Mid-month | Great Place to Work / Engagement Survey Launch | Virtual / Hybrid Event | Measure engagement, gather feedback | All employees | 4 weeks | EX Specialist, HR Analytics
December | 2nd/3rd week | Annual Awards Night / Recognition Gala | Large-Scale Flagship Event | Marquee recognition event, celebrate top performers | All employees (select outstation/onsite) | 8-10 weeks | EX Specialist, Leadership, Event Agency
December | 25 Dec | Christmas Celebration | In-house / Office-Level Event | Festive inclusion | All employees | 2-3 weeks | EX Specialist, Culture Committee
December | 31 Dec | Year-End Town Hall & Countdown Celebration | Live Show & Entertainment | Close the year, build excitement for next year | All employees | 4-6 weeks | EX Specialist, Leadership, Vendor/DJ
December | Any 2 weeks | CSR Toy / Blanket Donation Drive | Wellness & CSR Event | Community giving during winter/holiday season | Volunteers | 3 weeks | EX Specialist, CSR team, NGO partner

## Event Categories
Event Category Definitions
Use this classification to tag every event in the calendar and to pick the right checklist tab.
Category | Definition | Typical Scale | Typical Examples | Typical Budget Range (INR) | Planning Lead Time | Primary Owners
Large-Scale Flagship Event | Company-wide, high-visibility event, often with senior leadership involvement and external vendors. | 200+ attendees, multi-location | Annual Day, Foundation Day, Diwali Mega Celebration, Independence/Republic Day program, Awards Night, Family Day | ₹5,00,000 – ₹50,00,000+ | 8-12 weeks | EX Specialist, Admin/Facilities, Event Agency, Leadership
In-house / Office-Level Event | Low-key, team or floor-level event run mostly with internal resources. | <100 attendees, single floor/team | Birthday celebrations, mini festival celebrations, potlucks, desk decoration, small team outings | ₹0 – ₹50,000 | 1-3 weeks | EX Specialist / Coordinator, Office Admin
Live Show & Entertainment | Performance-led event involving external artists, DJs, comedians or performers, standalone or embedded in a larger event. | 50-1000+ attendees | DJ Night, Live Band, Stand-up Comedy, Dance Troupe performances at Diwali/Annual Day | ₹1,00,000 – ₹15,00,000 | 4-8 weeks | EX Specialist, Event Agency, Vendor/Artist Management, Security
Virtual / Hybrid Event | Event with a remote or streamed audience component, run over a digital platform. | Any size; unlimited remote reach | Town Halls, Webinars, Virtual Town Halls for global/remote teams | ₹0 – ₹2,00,000 | 2-4 weeks | IT/AV team, Internal Communications, EX Specialist
Wellness & CSR Event | Health, wellbeing or community-impact focused activity, often with an external partner/NGO. | Varies; opt-in participation | Yoga Day, Blood Donation Drive, Tree Plantation, Mental Health Workshops | ₹50,000 – ₹5,00,000 | 2-4 weeks | Wellness/CSR Partner, EX Specialist
Recognition & Rewards Event | Nomination or milestone-based program that culminates in a felicitation/ceremony. | Varies; ceremony can be 50-1000+ | Employee of the Month, Long Service Awards, Annual Awards Night | ₹1,00,000 – ₹20,00,000 | 4-6 weeks | HR/EX Specialist, Leadership, Finance

## Checklist - Large Scale Events
Checklist — Large-Scale Flagship Events
For company-wide events such as Annual Day, Foundation Day, Diwali Mega Celebration, Independence/Republic Day programs, Family Day and Awards Night.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 8-12 weeks before
1 | Pre-Event Planning | Define event objective, theme and success metrics | EX Specialist | 8-12 weeks before | Not Started
2 | Pre-Event Planning | Secure budget approval from Finance/Leadership | EX Specialist | 8-12 weeks before | Not Started
3 | Pre-Event Planning | Finalize date and confirm leadership/stakeholder availability | EX Specialist | 8-12 weeks before | Not Started
4 | Pre-Event Planning | Book venue (in-house or external) | Admin / Facilities | 8-12 weeks before | Not Started
5 | Pre-Event Planning | Shortlist and finalize event management agency/vendor | EX Specialist | 8-12 weeks before | Not Started
6 | Pre-Event Planning | Create event concept note and draft Run-of-Show (RoS) | EX Specialist | 8-12 weeks before | Not Started
7 | Pre-Event Planning | Plan guest list and invitee mapping (employees, families, VIPs) | HR / EX Specialist | 8-12 weeks before | Not Started
8 | Pre-Event Planning | Draft communication plan and send save-the-date | Internal Communications | 8-12 weeks before | Not Started
9 | Pre-Event Planning | Arrange stage, sound, lighting and decor | Vendor | 8-12 weeks before | Not Started
10 | Pre-Event Planning | Plan entertainment / artist bookings | EX Specialist / Vendor | 8-12 weeks before | Not Started
11 | Pre-Event Planning | Finalize catering and menu (incl. dietary options) | Admin / Vendor | 8-12 weeks before | Not Started
12 | Pre-Event Planning | Plan transportation/logistics for attendees | Admin | 8-12 weeks before | Not Started
13 | Pre-Event Planning | Coordinate security and crowd-management plan | Security / Admin | 8-12 weeks before | Not Started
14 | Pre-Event Planning | Arrange permissions/licenses (fire safety, sound permit, performer visas if any) | Admin / Legal | 8-12 weeks before | Not Started
15 | Pre-Event Planning | Plan photography/videography coverage | Internal Communications / Vendor | 8-12 weeks before | Not Started
16 | Pre-Event Planning | Design and order branding materials (banners, standees, backdrops) | Internal Communications / Vendor | 8-12 weeks before | Not Started
17 | Pre-Event Planning | Plan gifts, mementos and swag | Admin / EX Specialist | 8-12 weeks before | Not Started
18 | Pre-Event Planning | Set up registration process and RSVP tracking | HR / EX Specialist | 8-12 weeks before | Not Started
19 | Pre-Event Planning | Arrange event insurance coverage | Admin / Legal | 8-12 weeks before | Not Started
20 | Pre-Event Planning | Prepare contingency plan (weather, power backup, medical emergency) | Admin | 8-12 weeks before | Not Started
Mid-Prep / Final Readiness — 2-4 weeks before
21 | Mid-Prep / Final Readiness | Confirm final headcount and seating arrangement | EX Specialist | 2-4 weeks before | Not Started
22 | Mid-Prep / Final Readiness | Conduct venue site visit and technical rehearsal | EX Specialist / Vendor | 2-4 weeks before | Not Started
23 | Mid-Prep / Final Readiness | Finalize Run-of-Show with timings and speaker briefs | EX Specialist | 2-4 weeks before | Not Started
24 | Mid-Prep / Final Readiness | Send reminder communications to all invitees | Internal Communications | 2-4 weeks before | Not Started
25 | Mid-Prep / Final Readiness | Brief volunteers and event-day coordinators | EX Specialist | 2-4 weeks before | Not Started
26 | Mid-Prep / Final Readiness | Confirm all vendor contracts and payment schedules | Admin / Finance | 2-4 weeks before | Not Started
Event Day Execution — On the day
27 | Event Day Execution | Set up registration desk and welcome kits | EX Specialist / EX Team | On the day | Not Started
28 | Event Day Execution | Conduct sound/light check before doors open | Vendor / AV Team | On the day | Not Started
29 | Event Day Execution | Ensure medical/first-aid and security are on standby | Admin / Security | On the day | Not Started
30 | Event Day Execution | Manage guest flow and hospitality | EX Team | On the day | Not Started
31 | Event Day Execution | Execute program as per Run-of-Show | EX Specialist | On the day | Not Started
32 | Event Day Execution | Capture photos and videos | Internal Communications | On the day | Not Started
33 | Event Day Execution | Manage on-ground issue resolution | EX Specialist | On the day | Not Started
Post-Event Wrap-up — Within 1-2 weeks after
34 | Post-Event Wrap-up | Settle vendor payments | Finance / Admin | Within 1-2 weeks after | Not Started
35 | Post-Event Wrap-up | Send thank-you communication and event highlights | Internal Communications | Within 1-2 weeks after | Not Started
36 | Post-Event Wrap-up | Collect post-event feedback survey | EX Team | Within 1-2 weeks after | Not Started
37 | Post-Event Wrap-up | Prepare event report (attendance, budget vs. actual, learnings) | EX Specialist | Within 1-2 weeks after | Not Started
38 | Post-Event Wrap-up | Share photos/videos on internal channels and social media | Internal Communications | Within 1-2 weeks after | Not Started
39 | Post-Event Wrap-up | Conduct debrief meeting with stakeholders | EX Specialist | Within 1-2 weeks after | Not Started

## Checklist - In-house Events
Checklist — In-house / Office-Level Events
For team or floor-level events such as birthday celebrations, work anniversaries, mini festival celebrations and potlucks.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 1-2 weeks before
1 | Pre-Event Planning | Identify occasion and finalize date/time | EX Specialist / Coordinator | 1-2 weeks before | Not Started
2 | Pre-Event Planning | Get informal budget approval | EX Specialist / Coordinator | 1-2 weeks before | Not Started
3 | Pre-Event Planning | Book internal space (cafeteria/breakout area) | Office Admin | 1-2 weeks before | Not Started
4 | Pre-Event Planning | Plan simple decor (balloons, banners, theme props) | EX Coordinator | 1-2 weeks before | Not Started
5 | Pre-Event Planning | Order cake/snacks/refreshments | Office Admin | 1-2 weeks before | Not Started
6 | Pre-Event Planning | Send calendar invite / announcement on Slack/Teams/intranet | EX Coordinator | 1-2 weeks before | Not Started
7 | Pre-Event Planning | Arrange small games/activities if needed | EX Coordinator | 1-2 weeks before | Not Started
8 | Pre-Event Planning | Prepare small gifts/certificates if applicable | EX Coordinator | 1-2 weeks before | Not Started
Event Day Execution — On the day
9 | Event Day Execution | Set up venue and decor | EX Coordinator | On the day | Not Started
10 | Event Day Execution | Welcome and host the celebration | EX Coordinator | On the day | Not Started
11 | Event Day Execution | Capture photos for internal newsletter/intranet | EX Coordinator / Volunteer | On the day | Not Started
12 | Event Day Execution | Ensure cleanliness and timely wrap-up | Office Admin | On the day | Not Started
Post-Event Wrap-up — Within 2-3 days after
13 | Post-Event Wrap-up | Share photos on internal groups/newsletter | EX Coordinator | Within 2-3 days after | Not Started
14 | Post-Event Wrap-up | Log participation for engagement tracking | HR / EX Specialist | Within 2-3 days after | Not Started
15 | Post-Event Wrap-up | Collect quick informal feedback | EX Coordinator | Within 2-3 days after | Not Started

## Checklist - Live Shows
Checklist — Live Shows & Entertainment
For artist/performer-led entertainment such as DJ nights, live bands, stand-up comedy and dance troupes — standalone or embedded in a larger event.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 4-8 weeks before
1 | Pre-Event Planning | Define show theme/genre (music, comedy, dance) | EX Specialist | 4-8 weeks before | Not Started
2 | Pre-Event Planning | Shortlist and audition/finalize artists/performers | EX Specialist / Vendor | 4-8 weeks before | Not Started
3 | Pre-Event Planning | Negotiate artist contracts and fees | Admin / Finance | 4-8 weeks before | Not Started
4 | Pre-Event Planning | Confirm technical rider (sound, lighting, stage requirements) | AV Vendor | 4-8 weeks before | Not Started
5 | Pre-Event Planning | Book stage, sound and lighting equipment | Vendor | 4-8 weeks before | Not Started
6 | Pre-Event Planning | Arrange performer travel and accommodation (if outstation) | Admin | 4-8 weeks before | Not Started
7 | Pre-Event Planning | Obtain performance licenses/copyright clearances | Legal / Admin | 4-8 weeks before | Not Started
8 | Pre-Event Planning | Plan seating/stage layout and audience capacity | EX Specialist | 4-8 weeks before | Not Started
9 | Pre-Event Planning | Arrange security for artist and crowd control | Security | 4-8 weeks before | Not Started
10 | Pre-Event Planning | Plan emcee/host script and artist introductions | EX Specialist | 4-8 weeks before | Not Started
Mid-Prep / Final Readiness — 1-2 weeks before
11 | Mid-Prep / Final Readiness | Conduct sound check and rehearsal with artists | Vendor / AV Team | 1-2 weeks before | Not Started
12 | Mid-Prep / Final Readiness | Finalize show Run-of-Show with cue sheet | EX Specialist | 1-2 weeks before | Not Started
13 | Mid-Prep / Final Readiness | Brief backstage team and artist coordination point | EX Specialist | 1-2 weeks before | Not Started
14 | Mid-Prep / Final Readiness | Confirm green room / artist hospitality arrangements | Admin | 1-2 weeks before | Not Started
Event Day Execution — On the day
15 | Event Day Execution | Manage artist arrival and sound check | AV Team / Admin | On the day | Not Started
16 | Event Day Execution | Manage backstage logistics | EX Team | On the day | Not Started
17 | Event Day Execution | Execute show as per cue sheet | EX Specialist / Host | On the day | Not Started
18 | Event Day Execution | Handle live audience engagement | Host / EX Team | On the day | Not Started
19 | Event Day Execution | Capture professional photography/videography | Internal Communications | On the day | Not Started
Post-Event Wrap-up — Within 1-2 weeks after
20 | Post-Event Wrap-up | Settle artist/vendor payments | Finance | Within 1-2 weeks after | Not Started
21 | Post-Event Wrap-up | Collect performance rights documentation for archival | Legal | Within 1-2 weeks after | Not Started
22 | Post-Event Wrap-up | Share event highlights/reels on internal and social channels | Internal Communications | Within 1-2 weeks after | Not Started
23 | Post-Event Wrap-up | Debrief with vendor on technical/logistics feedback | EX Specialist | Within 1-2 weeks after | Not Started

## Checklist - Virtual-Hybrid
Checklist — Virtual / Hybrid Events
For town halls, webinars and any event with a remote or streamed audience component.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 2-4 weeks before
1 | Pre-Event Planning | Define objective and format (webinar, town hall, hybrid) | EX Specialist | 2-4 weeks before | Not Started
2 | Pre-Event Planning | Select streaming/broadcast platform (Teams/Zoom/YouTube Live) | IT | 2-4 weeks before | Not Started
3 | Pre-Event Planning | Test AV setup and internet bandwidth | IT / AV Team | 2-4 weeks before | Not Started
4 | Pre-Event Planning | Prepare content deck and speaker briefing | Internal Communications / EX Specialist | 2-4 weeks before | Not Started
5 | Pre-Event Planning | Schedule and send calendar invites to onsite and remote audience | EX Coordinator | 2-4 weeks before | Not Started
6 | Pre-Event Planning | Plan moderator role and Q&A management approach | EX Specialist | 2-4 weeks before | Not Started
7 | Pre-Event Planning | Set up hybrid venue (camera, mic, screen for remote link) | AV Vendor | 2-4 weeks before | Not Started
8 | Pre-Event Planning | Conduct technical rehearsal with speakers | IT / AV Team | 2-4 weeks before | Not Started
Event Day Execution — On the day
9 | Event Day Execution | Manage live streaming and recording | IT / AV Team | On the day | Not Started
10 | Event Day Execution | Moderate Q&A/chat interactions | EX Coordinator | On the day | Not Started
11 | Event Day Execution | Monitor technical issues in real time | IT | On the day | Not Started
Post-Event Wrap-up — Within 1 week after
12 | Post-Event Wrap-up | Share recording and key takeaways | Internal Communications | Within 1 week after | Not Started
13 | Post-Event Wrap-up | Collect feedback survey from onsite and remote attendees | EX Team | Within 1 week after | Not Started
14 | Post-Event Wrap-up | Analyze engagement metrics (attendance, watch time) | EX Specialist / IT | Within 1 week after | Not Started

## Checklist - Wellness & CSR
Checklist — Wellness & CSR Events
For health, wellbeing and community-impact activities such as Yoga Day, blood donation drives, tree plantation and mental health workshops.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 2-4 weeks before
1 | Pre-Event Planning | Identify wellness/CSR theme and partner NGO/vendor | EX Specialist | 2-4 weeks before | Not Started
2 | Pre-Event Planning | Get leadership and compliance approval | EX Specialist / Legal | 2-4 weeks before | Not Started
3 | Pre-Event Planning | Finalize date and venue/location (onsite/offsite) | EX Coordinator | 2-4 weeks before | Not Started
4 | Pre-Event Planning | Arrange certified trainers/medical staff (yoga instructor, doctors, blood bank team) | Vendor | 2-4 weeks before | Not Started
5 | Pre-Event Planning | Plan employee registration and consent forms (esp. blood donation/health checks) | HR / EX Specialist | 2-4 weeks before | Not Started
6 | Pre-Event Planning | Arrange logistics (mats, medical kits, refreshments) | Admin | 2-4 weeks before | Not Started
7 | Pre-Event Planning | Promote participation via internal communications | Internal Communications | 2-4 weeks before | Not Started
Event Day Execution — On the day
8 | Event Day Execution | Set up registration and health-screening desk | HR / Vendor | On the day | Not Started
9 | Event Day Execution | Conduct the wellness/CSR activity | Vendor / Trainer | On the day | Not Started
10 | Event Day Execution | Ensure medical support is on standby | Medical Team | On the day | Not Started
11 | Event Day Execution | Capture participation data and photos | EX Team | On the day | Not Started
Post-Event Wrap-up — Within 1-2 weeks after
12 | Post-Event Wrap-up | Share impact report (units of blood collected, trees planted, participants) | EX Specialist | Within 1-2 weeks after | Not Started
13 | Post-Event Wrap-up | Send appreciation certificates/notes to participants | EX Coordinator | Within 1-2 weeks after | Not Started
14 | Post-Event Wrap-up | Publish CSR impact story internally and on social media | Internal Communications | Within 1-2 weeks after | Not Started

## Checklist - Recognition
Checklist — Recognition & Rewards Events
For nomination-based recognition programs and awards ceremonies such as Employee of the Month, Long Service Awards and the Annual Awards Night.
S.No | Phase | Task | Owner / Responsible | Recommended Timeline | Status | Remarks / Notes
Pre-Event Planning — 4-6 weeks before
1 | Pre-Event Planning | Define award categories and nomination criteria | HR / EX Specialist | 4-6 weeks before | Not Started
2 | Pre-Event Planning | Open nomination window and collect entries | HR / EX Specialist | 4-6 weeks before | Not Started
3 | Pre-Event Planning | Form jury/panel for shortlisting | Leadership / HR | 4-6 weeks before | Not Started
4 | Pre-Event Planning | Finalize winners and get leadership sign-off | HR Lead | 4-6 weeks before | Not Started
5 | Pre-Event Planning | Order trophies, certificates and gifts | Admin | 4-6 weeks before | Not Started
6 | Pre-Event Planning | Plan award ceremony format (standalone or part of a larger event) | EX Specialist | 4-6 weeks before | Not Started
7 | Pre-Event Planning | Prepare winner citations and highlight videos/photos | Internal Communications | 4-6 weeks before | Not Started
8 | Pre-Event Planning | Invite winners' families/managers if applicable | EX Coordinator | 4-6 weeks before | Not Started
Event Day Execution — On the day
9 | Event Day Execution | Set up stage and award display | EX Team | On the day | Not Started
10 | Event Day Execution | Host the recognition ceremony | EX Specialist / Host | On the day | Not Started
11 | Event Day Execution | Capture winner moments (photo/video) | Internal Communications | On the day | Not Started
Post-Event Wrap-up — Within 1-2 weeks after
12 | Post-Event Wrap-up | Publish winner list and stories on internal channels | Internal Communications | Within 1-2 weeks after | Not Started
13 | Post-Event Wrap-up | Send certificates/soft copies to winners | HR | Within 1-2 weeks after | Not Started
14 | Post-Event Wrap-up | Update employee records with recognition history | HR | Within 1-2 weeks after | Not Started